## EVM
ID | Task Name | Cost ($) | Duration (Expected) |  | Duration (Actual) |  | Planned Value (PV) | PV (to date) | Actual costs (AC) | Rate of Performance (RP) | Earned Value (EV) | Schedule Variance (SV) | Cost Performance Index (CPI) | Schedule Performance Index (SPI)
1 | Lay foundations | 18000 | 2 | weeks | 2 | weeks | 18000 | 18000 | 18000 | 100% | 18000 | 0 | 100% | 100%
2 | Build frame | 34000 | 4 | weeks | 4 | weeks | 34000 | 34000 | 34000 | 100% | 34000 | 0
3 | Install pipes and electrical | 10000 | 6 | weeks | 6 | weeks | 10000 | 10000 | 10000 | 100% | 10000 | 0
4 | Make house water-tight | 15000 | 8 | weeks | 8 | weeks | 15000 | 15000 | 15000 | 100% | 15000 | 0
5 | Install internal walls and bathroom | 20000 | 12 | weeks | 12 | weeks | 20000 | 20000 | 20000 | 100% | 20000 | 0
6 | Install cabinetries | 14000 | 4 | weeks | 4 | weeks | 14000 | 14000 | 17500 | 80% | 11200 | -2800 | 68% | 85%
|  | Schedule overrun |  |  | 1 | weeks |  | 3500 |  | 20% | 700
7 | Paint house | 8000 | 2 | weeks | 2 | weeks | 8000 | 8000 | 10400 | 76.92% | 6153.8462 | -1846.1538 | 64.5% | 83.85%
|  | Schedule overrun |  |  | 0.6 | weeks |  | 2400 |  | 23.08% | 553.8462
8 | Install light fixtures and appliances | 9000 | 2 | weeks | 2 | weeks | 9000 | 9000 | 12600 | 71.43% | 6428.5714 | -2571.4286 | 59.18% | 82.86%
|  | Schedule overrun |  |  | 0.8 | weeks |  | 3600 |  | 28.57% | 1028.5714
| Project planned value (PV) | 128000 | 40 | weeks | 42.4 | weeks | 128000 | 137500 | 137500 |  | 123064.8352 | -4935.1648 | 89.5% | 96.14%

## Graph
Task
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
PV | 18000 | 34000 | 10000 | 15000 | 20000 | 14000 | 8000 | 9000
Cumulative PV | 18000 | 52000 | 62000 | 77000 | 97000 | 111000 | 119000 | 128000
AC | 18000 | 34000 | 10000 | 15000 | 20000 | 17500 | 10400 | 12600
Cumulative AC | 18000 | 52000 | 62000 | 77000 | 97000 | 114500 | 124900 | 137500
EV | 18000 | 34000 | 10000 | 15000 | 20000 | 11900 | 6707.6923 | 7457.1429
Cumulative EV | 18000 | 52000 | 62000 | 77000 | 97000 | 108900 | 115607.6923 | 123064.8352