## Risk Register
Project Risk Register
Project Name: |  | XYZ Project
Prepared By: |  | Fengdan Cui
Last Update: |  | 2022-04-16
Residual Risk
Risk ID | Risk Description (There is a risk that….caused by…..resulting in……) | Likelihood | Prob | Impact/ Concequence | Impact Score | Risk Level | Risk Rating | Current Controls | Strategy | Risk Treatment/ Response | $Cost | Future Controls | Likelihood | Prob | Impact/ Concequence | Impact Score | Risk Level | Risk Rating | Responsibiliy
1 | There is a risk that key resources required for this project will be allocated to another important project in the company which will result major budget and schedule issues. | Almost Certain | 85% | Major | 4 | Extreme | 3.4 | None | Mitigate | Get senior management commitment by providing backfill resources | 60 | Weekly senior mgt briefing | Unlikely | 30% | Major | 4 | Medium | 1.2 | Tom Brown
2 | There is a risk that necessary equipment cannot be acquired for project, resulting in project delay | Possible | 41% | Major | 4 | Medium | 1.64 | None | Avoidance | Gather requirements early and purchase in time | 0 | Monitor the usage of equipment fruently | Unlikely | 16% | Major | 4 | Low | 0.64 | Peter Watson
3 | There is a risk that requirements will be updated during development which will result in overspend and delay. | Possible | 45% | Catastrophic | 5 | High | 2.25 | None | Mitigate | Gather and analyse new requirements from customers in time and make change plan effectively | 100 | Project manager should communicate with customers fluently and make effective change plan | Unlikely | 12% | Catastrophic | 5 | Medium | 0.6 | Ben Man
4 | There is a risk that developers' knowledge cannot meet the development of project, resulting in qulity and budget issues. | Unlikely | 16% | Major | 4 | Medium | 0.64 | None | Avoidance | Hire skilled and experienced developers who aslo know related knowledge about the project | 90 | Training developers for related knowledge | Rare | 5% | Major | 4 | Medium | 0.2 | Sam Dunn
5 | There is a risk that the completed project cannot meet the standard which will result in quality issue. | Possible | 41% | Catastrophic | 5 | High | 2.05 | None | Avoidance | Improve the quality management | $0 | Make quality assessment for the project regularly | Rare | 7% | Catastrophic | 5 | Medium | 0.35 | Emma Hones
[7 empty] | 9.98 | [10 empty] | 2.99
ETM Consultancy and Training Pty Ltd | [17 empty] | RR - A

## Risk Likelihood
Risk Likelihood Table
Rating | Explanation | Probabilty Range
Almost Certain | The event will almost certainly occur in the timeframe of the project | 80-99.99%
Likely | The event is expected to occur in the timeframe of the project | 60-79.99%
Possible | The event may occur in the timeframe of the project | 40-59.99%
Unlikely | The event is unlikely to occur in the timeframe of the project | 15-39.99%
Rare | The event would rarely occur in the timeframe of the project | .01-14.99%
RR - B

## Risk Impact_Consequence
Risk Impact/Consequences Table
| Rating | Qualitative impact | Impact Score
| Catastrophic | This would seriously threaten the continuance of the project. Project 'Showstopper' | 5
| Major | This would have a significant effect on the project and could threaten it's continuance. | 4
| Moderate | Impact on the project but would not threaten its continuance. | 3
| Minor | Minimal impact on the project. | 2
| Insignificant | No significant impact on the project. | 1
RR - C

## Risk Level
Risk Rating Table
LIKELIHOOD
| IMPACT | Rare | Unlikely | Possible | Likely | Almost Certain
| Catastrophic | Medium | Medium | High | Extreme | Extreme
| Major | Low | Medium | Medium | High | Extreme
| Moderate | Low | Medium | Medium | Medium | High
| Minor | Low | Low | Medium | Medium | Medium
| Insignificant | Very Low | Very Low | Low | Low | Medium
RR - D